## Sheet1
Risk Assessment
Risk ID | Risk Description | Risk Outcome | Potential Impact | Likelihood | Mitigation needed? | Action taken
1 | Database is breached. | If the database is breached, the information of users can be stolen. This information can include email addresses and passwords. | User information may be released and sold by third parties | Low | Yes | The passwords will be hashed to ensure that they can’t be stolen successfully.
2 | Cross Site Request Forgery (CSRF) attack | An unauthorised command is executed on the webpage to modify or delete user information | User information may be modified or deleted from the database, disallowing users to access their accounts | Low | Yes | CSRF protection was added with use of a secret key
3 | Site overload | A large amount of users may be attempting to access the webpage may cause the servers to become overloaded. | The webpage may become unavailable for a long period of time. | Low | Yes | A production server was created using Gunicorn, where a number of workers can be increased to compensate for increased traffic.
4 | Procurement of equipment | There may be some form of obstruction that will delay in the gathering of required resources | Equipment necessary for the creation and running of the web application may not be available when required. | Medium | Yes | Alternative technologies were investigated that would allow for similar or identical results to be achieved.
5 | Incorrect information in records. | Users may accidentally submit incorrect information in any of the various forms. | Incorrect information may distort the results, leading to incorrect analysis of the information stored. | High | Yes | Added option to update records of the robot models and algorithms.
6 | Records vandalised by guest users | Information on the webpage may be maliciously changed. | Incorrect information may distort the results, leading to incorrect analysis of the information stored. | Medium | Yes | Records can only be added, updated or changed by users who have registered on the webpage.
7 | Server downage | The server may become inactive due to intentional or accidental damage. | The webpage will become inactive, not allowing for users to access the webpage and its features. | Low | No | Server is managed by third-party.